## Blank
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.1.1 | Project Charter Revisions |  |  |  |  | 0%
1.2 | Research |  |  |  |  | 0%
1.3 | Projections |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Guidelines |  |  |  |  | 0%
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 0%
2.2 | Budget |  |  |  |  | 0%
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort and Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%

## Example
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE | Capstone Prosjekt
PROJECT MANAGER | Bjarne, Ylli, Abdinasir, Severin
COMPANY NAME | USN
DATE | 2024-01-08
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Prosjektplanlegging (Sprint 0) |  | 2024-01-08 | 2024-01-29 | 21
1.1 | Finne prosjektmål og omfang | Alle | 2024-01-08 | 2024-01-13 | 5 | 100%
1.2 | Opprette tidsplan (gantt diagram) | Alle | 2024-01-13 | 2024-01-18 | 5 | 100%
1.3 | Koordinere med prosjektleder | Alle | 2024-01-18 | 2024-01-22 | 4 | 100%
1.4 | Oppstartsmøte | Alle | 2024-01-08 | 2024-01-09 | 1 | 100%
1.5 | Opprette backlog | Alle | 2024-01-09 | 2024-01-29 | 20 | 100%
1.6 | Dokumentasjon | Alle | 2024-01-22 | 2024-01-29 | 7 | 100%
1.7 | Milestone: Oblig 1 | Alle | 2024-01-08 | 2024-02-05 | 28 | 100%
2 | Sprint 1 |  | 2024-01-29 | 2024-02-19 | 21
2.1 | Sprint Backlog | Severin | 2024-01-29 | 2024-02-02 | 4 | 0%
2.2 | Sprint planlegging | Ylli | 2024-01-30 | 2024-02-02 | 3 | 0%
2.3 | Implementering | Abdinasir | 2024-02-02 | 2024-02-14 | 12 | 0%
2.4 | Sprint vurdering | Laurent | 2024-02-13 | 2024-02-15 | 2 | 0%
2.5 | Sprint retrospekt | Bjarne | 2024-02-15 | 2024-02-17 | 2 | 0%
3 | Sprint 2 |  | 2024-02-19 | 2024-03-11 | 21
3.1 | Sprint Backlog | Severin | 2024-02-19 | 2024-02-23 | 4 | 0%
3.2 | Sprint planlegging | Ylli | 2024-02-20 | 2024-02-23 | 3 | 0%
3.3 | Implementering | Abdinasir | 2024-02-23 | 2024-03-06 | 12 | 0%
3.4 | Sprint vurdering | Laurent | 2024-03-05 | 2024-03-07 | 2 | 0%
3.5 | Sprint retrospekt | Bjarne | 2024-03-07 | 2024-03-09 | 2 | 0%
3.6 | Milestonse: Oblig 2 | Alle | 2024-02-05 | 2024-03-04 | 28 | 0%
4 | Sprint 3 |  | 2024-03-11 | 2024-04-01 | 21
4.1 | Sprint Backlog | Abdinasir | 2024-03-11 | 2024-03-15 | 4 | 0%
4.2 | Sprint planlegging | Laurent | 2024-03-12 | 2024-03-15 | 3 | 0%
4.3 | Implementering | Bjarne | 2024-03-15 | 2024-03-27 | 12 | 0%
4.4 | Sprint vurdering | Alle | 2024-03-26 | 2024-03-28 | 2 | 0%
4.5 | Sprint retrospekt | Severin | 2024-03-28 | 2024-03-30 | 2 | 0%
4.6 | Miletstone: Oblig 3 | Alle | 2024-03-04 | 2024-04-01 | 28 | 0%
5 | Publisering og lansering |  | 2024-04-01 | 2024-04-22 | 21
5.2 | Gjøre nettsiden offentlig | Abdinasir | 2024-04-01 | 2024-04-03 | 2 | 0%
5.4 | Brukervennlighetstesting på studenter | Abdinasir | 2024-04-03 | 2024-04-07 | 4 | 0%
5.5 | Finne og rette opp feil | Laurent | 2024-04-07 | 2024-04-17 | 10 | 0%
5.6 | Sjekke at nettsiden er responsiv | Bjarne | 2024-04-17 | 2024-04-18 | 1 | 0%
5.7 | Fullføre rapport | Alle | 2024-04-01 | 2024-04-22 | 21 | 0%