## Blank
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter |  |  |  |  | 100%
1.1.1 | Project Charter Revisions |  |  |  |  | 0%
1.2 | Research |  |  |  |  | 0%
1.3 | Projections |  |  |  |  | 0%
1.4 | Stakeholders |  |  |  |  | 0%
1.5 | Guidelines |  |  |  |  | 0%
1.6 | Project Initiation |  |  |  |  | 0%
2 | Project Definition and Planning
2.1 | Scope & Goal Setting |  |  |  |  | 0%
2.2 | Budget |  |  |  |  | 0%
2.3 | Communication Plan |  |  |  |  | 0%
2.4 | Risk Management |  |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status & Tracking |  |  |  |  | 0%
3.2 | KPIs |  |  |  |  | 0%
3.2.1 | Monitoring |  |  |  |  | 0%
3.2.2 | Forecasts |  |  |  |  | 0%
3.3 | Project Updates |  |  |  |  | 0%
3.3.1 | Chart Updates |  |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  |  | 0%
4.2 | Quality Deliverables |  |  |  |  | 0%
4.3 | Effort and Cost Tracking |  |  |  |  | 0%
4.4 | Project Performance |  |  |  |  | 0%

## Example
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE | Capstone Prosjekt
PROJECT MANAGER | Bjarne, Ylli, Abdinasir, Severin
COMPANY NAME | USN
DATE | 2024-01-08
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Prosjektplanlegging |  | 2024-01-08 | 2024-01-29 | 21
1.1 | Finne prosjektmål og omfang | Alle | 2024-01-08 | 2024-01-13 | 5 | 70%
1.2 | Opprette tidsplan (gantt diagram) | Alle | 2024-01-13 | 2024-01-18 | 5 | 100%
1.3 | Koordinere med prosjektleder | Alle | 2024-01-18 | 2024-01-22 | 4 | 100%
1.4 | Oppstartsmøte | Alle | 2024-01-08 | 2024-01-09 | 1 | 100%
1.5 | Studere teori og begreper | Alle | 2024-01-09 | 2024-01-29 | 20 | 50%
1.6 | Dokumentasjon | Alle | 2024-01-22 | 2024-01-29 | 7 | 60%
1.7 | Milestone: Oblig 1 | Alle |  | 2024-02-05
2 | Design og layout |  | 2024-01-29 | 2024-02-10 | 12
2.1 | Utvikle visuell komposisjon | Severin | 2024-01-29 | 2024-02-03 | 5 | 0%
2,2 | Opprette designkonspter (Figma) | Ylli | 2024-02-01 | 2024-02-07 | 6 | 0%
2.3 | Opprette prototyper og wireframes | Abdinasir | 2024-02-01 | 2024-02-07 | 6 | 0%
2.4 | Dokumentasjon | Laurent | 2024-02-07 | 2024-02-10 | 3 | 0%
3 | Innhold og bilder |  | 2024-02-10 | 2024-02-19 | 9
3.1 | Samle informasjonsinnhold | Bjarne | 2024-02-10 | 2024-02-12 | 2 | 0%
3.2 | Skrive informasjon til nettsiden | Severin | 2024-02-11 | 2024-02-13 | 2 | 0%
3.3 | Redigere bilder/videoer | Ylli | 2024-02-12 | 2024-02-14 | 2 | 0%
3.4 | Dokumentasjon | Abdinasir | 2024-02-13 | 2024-02-15 | 2 | 0%
4 | Utvikling av nettsiden |  | 2024-02-19 | 2024-03-10 | 20
4.1 | Koding av nettsiden | Laurent | 2024-02-19 | 2024-03-09 | 19 | 0%
4.2 | Gjøre nettsiden responsiv | Bjarne | 2024-03-04 | 2024-03-08 | 4 | 0%
4.3 | Legge til funksjonaliteter | Severin | 2024-02-21 | 2024-02-28 | 7 | 0%
4.4 | Dokumentasjon | Ylli | 2024-03-04 | 2024-03-09 | 5 | 0%
4.5 | Milestonse: Oblig 2 |  |  | 2024-03-04
5 | Testing og feilretting |  | 2024-03-11 | 2024-04-01 | 21
5.1 | Brukervennlighetstesting på studenter | Abdinasir | 2024-03-11 | 2024-03-16 | 5 | 0%
5.2 | Finne og rette opp feil | Laurent | 2024-03-16 | 2024-03-29 | 13 | 0%
5.3 | Sjekke at nettsiden er responsiv | Bjarne | 2024-03-25 | 2024-03-29 | 4 | 0%
5.4 | Dokumentasjon | Severin | 2024-03-27 | 2024-03-31 | 4 | 0%
5.5 | Miletstone: Oblig 3 |  |  | 2024-04-01
6 | Publisering og lansering |  | 2024-04-01 | 2024-04-12 | 11
6,1 | Laste opp nettsiden til en server | Ylli | 2024-04-01 | 2024-04-04 | 3 | 0%
6,2 | Gjøre nettsiden offentlig | Abdinasir | 2024-04-05 | 2024-04-08 | 3 | 0%
6,3 | Dokumentasjon | Laurent | 2024-04-08 | 2024-04-12 | 4 | 0%
7 | Vedlikehold |  | 2024-04-12 | 2024-05-01 | 19
7,1 | Oppdatere funksjonalitet og behov | Bjarne | 2024-04-12 | 2024-04-20 | 8 | 0%
7,2 | Følge med på nettsiden | Severin | 2024-04-20 | 2024-04-26 | 6 | 0%
7,3 | Videreutvikle basert på tilbakemelding | Ylli | 2024-04-21 | 2024-04-30 | 9 | 0%
7,4 | Dokumentasjon | Abdinasir | 2024-04-27 | 2024-05-01 | 4 | 0%